## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | I want to ingest research paper data from pdf format,so that the data can be normalised and prepared for entity and relationship extraction | MUST HAVE | None | Arjun Choudhary | 3- Completed
Sprint 2 | Sprint 2 | US-01 | I want to transform the normalised JSON data into structured entities and relationships and construct a Neo4j knowledge graph so that research papers can be semantically queried and visualised. | MUST HAVE | Sprint 1 | Arjun Choudhary | 3- Completed
Sprint 3 | Sprint 3 | US-02 | I want to generate embeddings for research paper chunks and store them in a FAISS vector database so that relevant content can be retrieved using semantic search for the RAG pipeline. | MUST HAVE | Sprint 2 | Arjun Choudhary | 3- Completed
Sprint 4 | Sprint 4 | US-03 | I want to integrate a Hybrid RAG pipeline with a frontend interface where users can upload research papers, view summaries, and ask questions with confidence scores based on the research paper content. | MUST HAVE | Sprint 3 | Arjun Choudhary | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1 | Setup project structure and data folders | 2026-01-15 | 2026-01-15 | Arjun Choudhary | Development | Completed | 2
US-01 | T2 | Implement PDF parser for research papers | 2026-01-16 | 2026-01-17 | Arjun Choudhary | Development | Completed | 6
US-01 | T3 | Extract metadata (title, authors, year) from PDFs | 2026-01-18 | 2026-01-19 | Arjun Choudhary | Development | Completed | 5
US-01 | T4 | Split extracted text into sections and chunks | 2026-01-20 | 2026-01-21 | Arjun Choudhary | Development | Completed | 6
US-01 | T5 | Convert extracted data into normalized JSON format | 2026-01-22 | 2026-01-23 | Arjun Choudhary | Development | Completed | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty extracting structured text from research paper PDFs due to formatting differences. | Implemented text cleaning and parsing logic to normalize extracted content.
Sprint 1 | Day 4 | Metadata such as title and authors not consistently detected from PDF text. | Added rule-based extraction and fallback heuristics for metadata detection.
Sprint 2 | Day 2 | Neo4j connection failure during graph build execution. | Verified Neo4j server status and corrected Bolt connection configuration.
Sprint 2 | Day 4 | Duplicate nodes created while inserting data into Neo4j. | Replaced CREATE queries with MERGE to ensure idempotent graph creation.
Sprint 3 | Day 2 | OpenAI embedding API quota exceeded during embedding generation. | Switched to local embedding model (SentenceTransformers).
Sprint 3 | Day 4 | Difficulty integrating FAISS vector search with Node.js backend. | Implemented Python FastAPI microservice to handle FAISS operations.
Sprint 4 | Day 2 | Local LLM models required high system memory and failed to run. | Replaced heavy model with lightweight TinyLlama using Ollama.
Sprint 4 | Day 4 | RAG pipeline output initially available only through CLI. | Integrated frontend UI with backend APIs for user interaction.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-15 | 2026-01-28 | Arjun Choudhary | Started building PDF ingestion pipeline for research papers | Stopped manual data formatting | Continue improving data preprocessing scripts | Implemented automated PDF parsing and JSON normalization
2 | Sprint 2 | 2026-01-29 | 2026-02-11 | Arjun Choudhary | Started constructing Knowledge Graph in Neo4j | Stopped duplicate node insertion logic | Continue improving graph schema design | Implemented MERGE queries and fixed Neo4j connection issues
3 | Sprint 3 | 2026-02-12 | 2026-02-25 | Arjun Choudhary | Started embedding generation and FAISS vector search integration | Stopped using external API embeddings due to quota issues | Continue optimizing retrieval performance | Integrated SentenceTransformers embeddings and FAISS indexing
4 | Sprint 4 | 2026-02-26 | 2026-03-10 | Arjun Choudhary | Started implementing Hybrid RAG pipeline with LLM | Stopped CLI-only output testing | Continue improving response grounding and evaluation | Integrated TinyLlama model with RAG pipeline
5 | Sprint 4 | 2026-02-26 | 2026-03-10 | Arjun Choudhary | Started integrating frontend UI with backend services | Stopped manual testing through scripts | Continue improving user interaction features | Connected upload, summary, and Ask-AI pages with backend APIs
6 | Sprint 4 | 2026-02-26 | 2026-03-10 | Arjun Choudhary | Started implementing confidence score and evaluation metrics | Stopped returning answers without validation | Continue improving RAG reliability | Added retrieval score, groundedness score, and final confidence calculation