## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Arjun Choudhary | 2026-01-20 | in json format less number of entities where there | Sprint 1 | Arjun Choudhary | Logical | searched for more suitable entities and updated the json | 2026-01-21 | Closed | issue resolved and proper json was created
2 | Arjun Choudhary | 2026-02-09 | Neo4j connection failure (ECONNREFUSED 127.0.0.1:7687) during graph build execution. | Sprint 2 | Arjun Choudhary | Maintainability | Verified Neo4j server status, corrected Bolt URL and encryption settings (ENCRYPTION_OFF). | 2026-02-10 | Closed | Verified Neo4j server status, corrected Bolt URL and encryption settings (ENCRYPTION_OFF).
3 | Arjun Choudhary | 2026-02-09 | Duplicate nodes created in Neo4j due to use of CREATE instead of MERGE. | Sprint 2 | Arjun Choudhary | Logical | Replaced CREATE queries with MERGE for idempotent node creation. | 2026-02-10 | Closed | Graph now prevents duplication and maintains consistency.
4 | Arjun Choudhary | 2026-02-09 | Missing relationship parameter error (Expected parameter(s): subject). | Sprint 2 | Arjun Choudhary | Logical | Missing relationship parameter error (Expected parameter(s): subject). | 2026-02-10 | Closed | Corrected parameter names in Cypher queries to match JSON structure
5 | Arjun Choudhary | 2026-02-10 | Relationship creation executed successfully after fix. | Sprint 2 | Arjun Choudhary | Logical | Verified relationship direction and ensured REPRESENTS_PART_OF query executed correctly. | 2026-02-10 | Closed | Graph now displays correct semantic structure.
6 | Arjun Choudhary | 2026-02-24 | OpenAI embedding API returned quota exceeded error (429) during embedding generation. | Sprint 3 | Arjun Choudhary | Maintainability | Replaced OpenAI embedding API with local SentenceTransformers model (all-MiniLM-L6-v2). | 2026-02-24 | Closed | System now generates embeddings locally without API dependency.
7 | Arjun Choudhary | 2026-02-25 | FAISS vector search not directly supported in Node.js environment. | Sprint 3 | Arjun Choudhary | Logical | Implemented Python FastAPI microservice to handle FAISS vector operations and connected using Axios. | 2026-02-26 | Closed | Hybrid architecture successfully enabled vector retrieval.
8 | Arjun Choudhary | 2026-02-25 | LLM generating hallucinated answers for irrelevant queries. | Sprint 3 | Arjun Choudhary | Logical | Implemented retrieval precision check before invoking LLM and added strict grounding prompt. | 2026-02-26 | Closed | System now avoids answering unrelated questions.
9 | Arjun Choudhary | 2026-02-28 | CLI-based RAG pipeline output not accessible for end users. | Sprint 4 | Arjun Choudhary | User Interface | Integrated frontend interface using HTML, CSS, and JavaScript with Express API endpoints. | 29-02-2026 | Closed | Users can now upload papers, view summaries, and ask questions through UI.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others